## Slide 1
PROPOSED COMMERCIAL POSITION | DECISION REQUIRED
A differentiated $800k offer: automation first, QA by design
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
01
CUSTOMER SELLING PRICE
$800k
Illustrative target bid
MAX. DELIVERY BUDGET
$640k
Includes factory and QA/QC
TARGET GROSS PROFIT
$160k
20% gross margin
WE SELL A CONTROLLED INFORMATION OUTPUT
Process the complete agreed document and tag population using AI + deterministic rules
Apply automated QA/QC across every applicable record and batch
Add targeted, risk-based engineering and document-control reviews
GATING CONTRACTUAL ISSUE
The original tender asks the contractor to validate relationships. Customer-owned final verification and a capped review scope require explicit agreement.
The offer is outcome-led, but the outcome must be precisely defined and contractually accepted.
Notes: [Sources] Oman LNG Scope of Work v2 (SOW), sections 3, 10-13, 16-20, 24, 27-30. Commercial assumptions inherited from prior internal scenario discussion: $800k customer price; 20% gross margin; $640k maximum delivery budget. Scope and acceptance shift is a proposed variation, not confirmed by Oman LNG.

## Slide 2
OMAN LNG | AI-FIRST INFORMATION FACTORY
Three commercial choices — only one sits at $800k
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
02
OPTION
PRICE / APPROACH
CUSTOMER CONSEQUENCE
A / Factory-only
$400k fixed target
Candidate links and evidence; customer performs engineering verification and most QA.
B / Factory + QA/QC
$800k fixed target
Full automated QA; capped 4,800 paid reviewer hours and targeted independent assurance.
C / Full SOW outcome
Reprice after pilot
Contractor owns agreed engineering validation and full acceptance obligations; likely materially higher.
RECOMMENDATION Offer option B, conditional on documented customer decision rights and a hard QA review cap.
Notes: [Sources] SOW sections 16-18, 24-25, 27-30. Option A and B are alternative contracting models requiring approval, rather than representations that the original SOW can be met at either price. Option C must be independently priced after pilot; no definitive full-SOW price is claimed.

## Slide 3
OMAN LNG | AI-FIRST INFORMATION FACTORY
An industrial processing task — not 150,000 individual jobs
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
03
DOCUMENT ESTATE
≤150k
Mixed native, PDF, scans, CAD
CMMS ASSET TAGS
250–300k
Source asset-register extract
PI HISTORIAN TAGS
~50k
Plus prior fuzzy-match candidates
FACTORY PRODUCES
Document metadata, searchable derivatives, tag sightings
PI-to-CMMS and document-to-tag candidate registers
Evidence, confidence, lineage, reconciliation and exception status
QUALITY DEFINED BY
Coverage and source-accounting completeness
Measured precision AND recall, using customer-approved gold samples
Unambiguous split of machine results vs reviewed / accepted
Unknowns that drive cost: page count; native drawing support; number of tag sightings and relationships; revision conflicts.
Notes: [Sources] SOW sections 2 (indicative scope), 6-13 (work packages), 16-19 (pilot, QA, delivery). The 150k / 250-300k / 50k counts refer to different entities and cannot be added to estimate review effort. The exact page count, proportion of supported native drawings and candidate-relationship volume are unknown.

## Slide 4
OMAN LNG | AI-FIRST INFORMATION FACTORY
AI information factory — deterministic controls + targeted reasoning
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
04
01 / CONTROL
Receipts, inventory,
hashes and source
snapshot
›
02 / EXTRACT
Native text, OCR,
CAD readers and
metadata
›
03 / IDENTIFY
Engineering tag
sightings, aliases,
revision rules
›
04 / MATCH
CMMS/PI candidates,
unit/train logic,
selective LLM
›
05 / PACKAGE
AIM-ready datasets,
evidence, exceptions,
reconciliation
CROSS-CUTTING QUALITY GATES
Machine checks on 100% of applicable records
Risk-based engineering review + client decisions
Notes: [Sources] SOW sections 6-13, 17-20, 21-22. No new asset hierarchy or knowledge graph (sections 2 and 4). Preserve originals and generate separate searchable derivatives (section 8). AI must be deployed only in an Oman LNG-approved environment; use no public/consumer model ingestion. A high-reasoning LLM is for ambiguous candidates, not full-population brute-force inference.

## Slide 5
OMAN LNG | AI-FIRST INFORMATION FACTORY
QA/QC: coverage is universal; engineering review is targeted
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
05
AUTOMATED QA / QC
100% of applicable records and batches
Inventory, hash and batch count reconciliation
Tag existence, format, duplicate and train/unit rules
Revision and document evidence consistency
PI-to-CMMS match constraints / candidate scoring
Schema, controlled values, identifiers and trial-load checks
HUMAN ASSURANCE
4,800 paid review hours (budget assumption)
Stratified gold-standard testing: precision and recall
Technical risk checks for ambiguous and high-impact links
Separate reviews for PI mapping and document metadata
QA lead calibrates reviewers and controls decisions
Unresolved engineering decisions escalated to customer
Automated checks do NOT imply 100% accuracy; customer-defined thresholds and acceptance authority are mandatory.
Notes: [Sources] SOW sections 10-13 (engineering context and evidence), 16-18 (pilot, gold set, precision/recall, expert review), 19-20 (AIM schema, trial load), 28 (acceptance). "100%" refers to an attempt to apply defined automated checks to all eligible delivered records, not a guarantee of perfect extraction or successful processing. Manual review hours are an estimate priced at $50/hour.

## Slide 6
OMAN LNG | AI-FIRST INFORMATION FACTORY
Three data-quality scenarios affect assurance yield
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
06
SCENARIO
STRONG CANDIDATES*
REVIEW CAPACITY**
CUSTOMER EXPOSURE
DECENT
85–95%
27k–43k
Mostly reliable native data; QA can cover many at-risk links.
HYBRID
60–80%
18k–27k
Scans and inconsistent naming; material unresolved queue remains.
REALLY BAD
25–50%
8.6k–14.4k
Many ambiguous or unreadable records; most exceptions require customer disposition.
* Hypothetical high-confidence candidate share, NOT measured accuracy or engineering acceptance. ** Assumes 3,600 productive hours and 5–25 min / review.
Notes: [Sources] Planning assumptions only. "Strong candidates" 85-95%, 60-80%, 25-50% are not validated acceptance or precision rates. 4,800 paid reviewer hours times 75% casework productivity = 3,600 productive hours. Potential reviews: decent 3,600*60/(8 to 5) = 27,000-43,200; hybrid (12 to 8 minutes) = 18,000-27,000; really bad (25 to 15 minutes) = 8,640-14,400. Figures are capacity ceilings if all productive hours were used for same-type review, not commitments; a comprehensive QA plan also needs stratified gold sampling and document-level recall measurement. An unresolved case may be recorded with approved disposition.

## Slide 7
OMAN LNG | AI-FIRST INFORMATION FACTORY
The incremental $320k buys real specialist QA/QC capacity
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
07
ENGINEERING / DOCUMENT REVIEWERS
4,800 paid hours @ $50/h
$240k
SENIOR QA/QC LEAD
600 hours @ $70/h
$42k
AUTOMATED QA RULES + DASHBOARDS
Build tests, metrics, defects
$25k
INDEPENDENT REPORTING / TRIAL LOAD
Quality reports and load support
$13k
4,800 paid hours × 75% planning productivity = 3,600 effective case-review hours
Notes: [Sources] Budget assumption from preceding discussion: reviewers $240,000 = 4,800h x $50; lead $42,000 = 600h x $70; automation QA $25,000; independent quality and trial load $13,000; sum $320,000. Rates are illustrative charge-out rates, not L&T bids. 75% casework productivity is a newly conservative planning assumption, not historical performance. The base factory still includes its own defect-correction reserve; no separate contingency exists inside the incremental $320k, requiring change-control protections.

## Slide 8
OMAN LNG | AI-FIRST INFORMATION FACTORY
Commercial bridge: $400k factory → $800k factory + assurance
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
08
Factory labour & configuration
$230.4k
OCR / models / compute & licences
$45.0k
Security, interfaces & trial-load support
$12.0k
Base factory contingency / rework
$32.6k
Engineering / document reviewers
$240.0k
Senior QA lead
$42.0k
Automated QA engineering
$25.0k
Independent QA reporting
$13.0k
FACTORY $320k
QA / QC $320k
BID PRICE $800k
Notes: [Sources] Factory cost base inherited from the $400k alternative: India-led labour $230.4k, OCR/model/compute $45k, security and integration $12k, factory contingency $32.6k = $320k. QA components $240k + $42k + $25k + $13k = $320k. Total cost ceiling $640k; customer selling price $800k; gross profit $160k or 20% margin on sale. Cost allowances are assumptions and not provider bids. No source-data remediation included. Only $32.6k contingency exists in combined baseline (5.1% of cost), so risk-sharing and stop/go are essential.

## Slide 9
OMAN LNG | AI-FIRST INFORMATION FACTORY
Technology is a cost and compliance decision — not a model contest
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
09
LAYER / OPTION
PREFERRED ROLE
DECISION TO VALIDATE
Rules + native readers
Bulk extraction; format-specific parsing; regex; exact/alias checks
Must be primary throughput engine.
Private enterprise LLM
Reasoning on conflicted metadata and ambiguous tags
Oman LNG-approved endpoint, residency, retention, cost.
Self-hosted open weights
Possible sensitive-data local inference (e.g., Llama/Qwen/Mistral)
GPU/infrastructure cost and quality compared in pilot.
AHA/IDB, DataGate, RDL
Potential standards / staging / bulk-loading reuse
Current support, licences and applicability unknown.
No public/consumer AI uploads; no new standalone asset hierarchy or knowledge graph under the base tender.
Notes: [Sources] SOW sections 2, 4 (no new asset hierarchy / knowledge graph), 21 (disclose software, models and locations), 22 (no public/consumer AI; approval of processing environments, subcontractors and data handling), 23 (IP). Shell AHA/IDB internal documentation discussed previously is historical; do not assume technical readiness. RDL/DataGate are proposed reuse candidates, not approved Oman LNG components. No model performance commitments without a pilot.

## Slide 10
OMAN LNG | AI-FIRST INFORMATION FACTORY
Where we must negotiate the acceptance boundary
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
10
EXCLUDED: CUSTOMER SOURCE REMEDIATION
No changes to CMMS or PI source records
No repair of original drawings / engineering redlining
No new tags or redesign of existing hierarchy
Unsupported or unreadable files must still be dispositioned
STILL REQUIRED: OUR OWN DEFECT CORRECTION
Fix extraction, formatting, lineage or schema defects
Retain evidence and reconcile every source record
Support an AIM trial load and correct rejected outputs
Satisfy agreed pilot QA and batch acceptance conditions
Formal clarification needed: cap contractor reviews and assign Oman LNG final engineering sign-off / exception decisions.
Notes: [Sources] SOW section 4.2 excludes modifications to original source documents, CMMS and PI tags, creating tags, redlining, changes to hierarchy. SOW section 15 requires approved exception dispositions; section 16 mandatory pilot; section 18 competent human validation; section 20 contractor correction of trial-load issues; section 28 rejects untraceable/incomplete outputs and requires correction/resubmission at no extra cost of contractor-caused noncompliance; sections 29-30 payment and change control. The tender does NOT appear to exempt the contractor from correcting its own output defects.

## Slide 11
OMAN LNG | AI-FIRST INFORMATION FACTORY
Pilot-gated delivery makes the risk priceable
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
11
0 / CLARIFY
Approve alternative RACI, QA cap, acceptance, source snapshot and permitted AI processing.
1 / PILOT
Stratify by format, age, train and quality; establish gold samples, recall / precision and cost.
2 / GATE
Confirm page and candidate volumes, QA capacity, output schema and scenario classification.
3 / FACTORY
Process controlled batches, monitor auto QA, review priority cases and publish exception registers.
4 / HANDOVER
Trial load; correct our outputs; transfer records, evidence, QA statistics and open dispositions.
No full-scale production before customer approval of the pilot quality plan and output model (SOW §16).
Notes: [Sources] SOW sections 5 (gold standard and reference inputs), 16 (mandatory proof-of-concept and full-scale go/no-go), 17 (separate precision / recall / metadata measures), 19-20 (AIM target and trial-load support), 28-30 (batch acceptance and change control). Proposed stage timing and QA cap are internal assumptions.

## Slide 12
RISK MANAGEMENT | INDICATIVE INHERENT ASSESSMENT
Top risks (1/2): deal structure and information uncertainty
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
12
RISK / CONSEQUENCE
LIK.
IMP.
PREVENT / MITIGATE
RESPONSE IF REALISED
R01 Scope deviation rejected; $800k bid non-compliant
H
Critical
Obtain written alternative-bid and QA/RACI approval
Rebid full scope, price a separate option, or no-bid.
R02 Low source quality overwhelms OCR and review capacity
H
Critical
Pilot quality strata incl. historical scans and CAD
Quarantine failures; rebaseline scope / approved variation.
R03 Pages or links exceed the priced population
M
High
Baseline page, sheet, composite and relation counts
Tiered overage fees; batch change-control / schedule extension.
R04 Incorrect train or unit links create unsafe relationships
H
High
Approved tagging philosophy, checks and blind QA samples
Hold affected batches; tune rules; rerun + re-QA.
L = Low; M = Medium; H = High. Ratings are qualitative starting assumptions, not quantified probabilities.
Notes: [Sources] Risk assessment is internal judgment; it is not sourced performance statistics. Relevant tender clauses: section 16 pilot approval; sections 10,13 context-sensitive tag and PI matching; sections 2,6 source volumes; sections 27-30 acceptance and change control. Risk mitigations describe prevention; response describes remedial action after occurrence, excluding unapproved source-system alterations. More risks and owners in accompanying Word decision paper.

## Slide 13
RISK MANAGEMENT | INDICATIVE INHERENT ASSESSMENT
Top risks (2/2): quality proof, cyber, customer decisions
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
13
RISK / CONSEQUENCE
LIK.
IMP.
PREVENT / MITIGATE
RESPONSE IF REALISED
R05 False negatives missed by candidate-only QA
M
High
Independent document-level gold samples for recall
Tune readers; targeted rerun and root-cause report.
R06 AI / data residency or subcontractor approval fails
M
Critical
Approve environment, location, terms before transfer
Stop processing; containment and approved architecture switch.
R07 Customer sign-off and exception decisions stall
H
High
Named owner, decision SLA and bulk disposition policy
Escalate queue, adjust gates and schedule through change-control.
R08 AIM load-ready outputs rejected due to our defect
M
High
Early target mapping, automated schema tests, trial load
Correct deliverables and resubmit within agreed scope.
Full 16-risk register in Word: likelihood, impact, triggers, owners, preventive controls and corrective responses.
Notes: [Sources] SOW sections 17 (separate detection precision and recall), 18 (competent human validation), 19-20 (AIM and trial-load correction), 22 (AI restrictions and approved environments), 24-25 (party roles), 28-30 (formal acceptance and change control). Ratings illustrative.

## Slide 14
INTERNAL DECISION | PROPOSED NEXT STEPS
Decisions for the bid leadership team
INTERNAL BID STRATEGY | COMMERCIAL ASSUMPTIONS TO BE CONFIRMED
14
Approve the $800k option only if we can secure:
An explicit customer-approved split of engineering verification and exception disposition
A controlled dataset baseline, capped reviewer hours and change/overage mechanism
A stratified pilot establishing precision, recall, review-time and cost assumptions
A permitted secure AI environment and a gold-standard sample
Acceptance gates based on evidenced, usable outputs — plus correction of our own defects
GO if these conditions are accepted. REPRICE or offer full-SOW alternative if Oman LNG requires comprehensive engineering validation.
Notes: [Sources] Internal recommendation based on SOW sections 16-18, 22, 24-25, 28-30 and commercial model. No customer approval is known. Corresponding Word document includes decision register, contractual clauses, risk owners and recommended pilot acceptance metrics.