OMAN LNG  |  INTERNAL BID STRATEGY

# AI-First Information Factory
and Engineering QA/QC

Commercial options, operating model, decision consequences and risk register

Version 2.0  •  15 October 2026

| TARGET CUSTOMER PRICE | DELIVERY BUDGET | TARGET GROSS PROFIT |
| --- | --- | --- |
| $800,000 | $640,000 | $160,000 (20%) |

## Strategic proposition

Use a reusable extraction-and-matching factory to process Oman LNG engineering documents, CMMS tags and PI Historian tags at industrial scale. Apply automated technical quality checks to the complete agreed population, augmented by targeted engineering and document-control review. Transfer unresolved technical adjudication to named Oman LNG decision owners only if explicitly accepted by the customer.

Proposed bid structure: $320k factory cost + $320k incremental QA/QC cost + $160k gross profit = $800k customer price.

## Status and use

This is an internal commercial and technical decision paper. The $800k alternative, rates, productivity, confidence scenarios, QA cap and programme duration are planning assumptions. No customer-approved scope deviation, subcontractor quotation or measured Oman LNG quality baseline has been established.

## Source basis

Primary source: Oman LNG, “Scope of Work v2” (41 pages). References throughout identify source sections. All commercial values, proposed responsibility transfers and performance ranges are separately labelled as internal hypotheses.

Table of Contents

Strategic proposition	1

Status and use	1

Source basis	1

1. Executive recommendation	5

2. Evidence base, assumptions and unknowns	6

2.1 SOW facts that shape the offer	6

2.2 Working commercial and technical assumptions (not tender facts)	6

2.3 Material unknowns requiring discovery	6

3. Commercial delivery options and their consequences	7

3.1 Why the $800k option is distinct	7

3.2 Consequences of selecting each option	7

4. Exactly what the factory delivers	8

4.1 Workflow and processing logic	8

Controlled receipt	8

Parallel extraction	8

Semantic extraction	8

Candidate linking	8

Quality gates	8

Batch outputs	8

4.2 Minimum evidence and disposition contract	8

4.3 What is outside source-remediation scope	8

5. AI, technology and platform choices	9

5.1 Do not use expensive reasoning for commodity extraction	9

5.2 Hosting/model options	9

5.3 Reuse candidates: AHA/IDB, RDL Explorer and DataGate	9

6. QA/QC design and meaningful acceptance metrics	10

6.1 Automated checks applied across the agreed population	10

6.2 Independent manual assurance - four sampling strata	10

6.3 Acceptance categories must not be conflated	10

6.4 Suggested pilot measures	10

7. Review capacity and three data-quality scenarios	12

7.1 Paid time versus useful review output	12

7.2 Why 500,000 candidate relationships changes the interpretation	12

7.3 Scenario-specific consequences and commercially sensible responses	12

Decent: mostly native, searchable and consistent	12

Hybrid: mixed searchable, raster, historical and conflicting data	12

Really bad: poor scans, unsupported native formats and unreliable reference data	12

8. Bottom-up commercial model	13

8.1 Base factory - $320,000 estimated cost	13

8.2 Incremental assurance - $320,000 estimated cost	13

8.3 Margin, not markup	13

8.4 Optional extension economics	13

9. People, roles and accountabilities	15

10. Delivery plan, gates and acceptance	16

10.1 Proposed milestone weighting (negotiable)	16

10.2 Stop/go and change-control triggers	16

11. Tender qualifications, safeguards and key decisions	17

11.1 Wording needed in an alternative offer	17

Contracted deliverable	17

Responsibility split	17

Review-hour ceiling	17

Volume and format envelope	17

Defect correction	17

AI / information restrictions	17

Pilot thresholds and change mechanism	17

11.2 Consequence of failing to obtain the deviations	17

12. Risk management framework	18

13. Detailed risk register	19

R01  Tender deviation or capped validation rejected	19

R02  Document estate far worse than pilot sample	19

R03  Physical pages and relationship rows far exceed assumed quantities	19

R04  False positive technical mappings, including train crossovers	20

R05  False negatives hidden by a candidate-only review	20

R06  Oman LNG data security, AI usage or India subcontractor approval fails	20

R07  Customer engineering decisions and approvals are slow	20

R08  AIM target schema or trial load reveals our deliverable defects	21

R09  OCR, inference and GPU/cloud costs exceed $45k allowance	21

R10  Legacy/proprietary CAD and composite files cannot be read	21

R11  Inadequate reference data, tag philosophy or gold-standard labels	21

R12  Source data refresh, late additions and revision drift	22

R13  QA reviewer rate, availability or productivity assumptions fail	22

R14  Insufficient headroom for contractor-caused output rework	22

R15  Intellectual property, third-party licences or platform reuse blockers	22

R16  Client cannot accept unresolved status or capped quality warranty	23

14. Risk response by data-quality scenario	24

Decent	24

Hybrid	24

Really bad	24

Catastrophic acceptance or security deviation	24

15. Tender clarifications to submit	25

Scope, volumes and reference data	25

Technical acceptance and responsibilities	25

AI, environment, platforms and IP	25

Commercial, governance and timing	25

16. Decision log and next actions	26

Proposed immediate next actions	26

17. Appendix — tender traceability and terminology	27

Acronym guide	27

Source and limitations	27

# 1. Executive recommendation

Recommend preparing a priced alternative offer for $800k, built around an AI-first production factory and a capped specialist QA/QC service, while retaining a separate pathway to price the original fully validated SOW after a representative pilot. This may align with reported customer interest in AI-first rather than labour-intensive delivery; that interest is not written contractual approval.

The factory should run native extraction, OCR where necessary, engineered tag matching, selective LLM reasoning, quality rules, evidence capture and complete source reconciliation in controlled batches.

The QA uplift buys 4,800 paid specialist review hours, 600 senior QA-lead hours, QA automation and independent reporting / trial-load support. It must NOT be construed as individual verification of every relationship.

The customer must approve the revised decision-rights and acceptance model. The SOW presently holds the contractor accountable for engineering validation and allows rejection if quality, traceability or load readiness are deficient.

The commercial mechanism must cap source quantities and effort, and provide paid variations for extra pages, formats, candidate records, reprocessing beyond contractor-caused defects and extended engineering validation.

Decision rule: proceed at $800k only with an accepted alternative scope, pilot-calibrated quality plan, secure processing approval and a fixed QA review-hour ceiling.

# 2. Evidence base, assumptions and unknowns

## 2.1 SOW facts that shape the offer

| Source-derived requirement | Where in SOW | Implication for the bid |
| --- | --- | --- |
| Up to 150,000 technical documents; 250k–300k CMMS tags; ~50k PI tags | §2 | Counts are indicative; final source extracts define actual population. |
| Native / scanned / CAD files; composite vendor documentation | §§2, 7–8 | Need format-based extraction lanes and page / sheet inventory. |
| Validated document-to-tag and PI-to-CMMS relationships | §§10–13 | Engineering sign-off cannot silently be reassigned. |
| Mandatory pilot and quality measures including recall | §§16–17 | No credible quality warranty without approved reference samples. |
| Competent engineering review and controlled exceptions | §§15, 18 | Capped QA is a potential deviation from original scope. |
| Structured AIM-aligned output and representative trial load | §§19–20 | Schema validation, load trial and correction of our defects remain. |
| No public consumer AI / customer-approved processing | §22 | Data location, services, telemetry and subcontractors need approval. |
| Contractor responsible for acceptance and corrections | §§24, 28–30 | Alternative acceptance / payment clauses must be negotiated. |

## 2.2 Working commercial and technical assumptions (not tender facts)

$800k customer price, 20% gross margin; $640k delivery cost ceiling. Delivery cost means provider / labour / infrastructure / contingency allowances, not fully loaded company net profit.

The prior $400k factory scenario has a cost base of $320k. An additional $320k is assumed available for QA/QC in the $800k proposition.

An initial six-month factory duration plus pilot and acceptance scheduling is a hypothesis, not a contractual programme; dependent on source access, processing environments and client decisions.

A 75% productive case-review factor is applied to the 4,800 paid reviewer hours; the remaining 25% covers calibration, training, record retrieval, documentation, reviewer coordination and other overheads.

Illustrative candidate high-confidence proportions are 85–95% (decent), 60–80% (hybrid), and 25–50% (really bad). These are not measured accuracy, recall or accepted relationship percentages.

## 2.3 Material unknowns requiring discovery

Unknowns include number of pages/sheets and composite subdocuments, percentage of raster vs native files, supportability of native CAD applications, proportion of unique vs repeated tags, number of candidate relationship rows, PI-to-CMMS candidate quality, quality and availability of target AIM templates, permitted AI processing architectures, and turnaround of customer engineering decisions.

# 3. Commercial delivery options and their consequences

| Option | Indicative customer price | Scope of supplier responsibility | Consequence / caveat |
| --- | --- | --- | --- |
| A. Factory only | $400k | Controlled extraction, candidate mapping, evidence, automated QA and exception reporting. | Customer carries nearly all human engineering QA; alternative to original SOW. |
| B. Factory + QA/QC (preferred) | $800k | Option A plus capped human assurance, QA lead, independent testing and AIM load checks. | Meaningful QA but not verification of all links; client adjudicates unresolved cases by agreement. |
| C. Original fully validated SOW | To be repriced after pilot | Supplier provides appropriate engineering review to satisfy original acceptance and closure obligations. | Potentially materially higher price; avoid fixed commitment until volumes and quality are known. |
| D. Modular $800k + review increments | $800k base + change orders | Option B plus extra paid QA units after trigger / approval. | Flexible under really bad quality; requires transparent change control and clear customer budget ceiling. |

## 3.1 Why the $800k option is distinct

The offer is neither a low-cost engineering-body-shop proposal nor a statement that a single LLM can validate all documents. It is a repeatable software-led conversion and reconciliation service, priced by an agreed source population and quality protocol. People are used primarily to validate model performance, resolve high-consequence cases and provide a defendable evidence trail.

## 3.2 Consequences of selecting each option

Choose A:  lower entry price, but the client must fund a material engineering review capability and accept a greater backlog of unresolved candidates. Lower delivery cost does not imply lower total ownership cost.

Choose B:  more quality evidence and smaller customer investigation burden. Still needs an approved limit on contractor human verification and an agreed final engineering-sign-off RACI.

Choose C:  best alignment to unmodified SOW, but likely requires a much larger specialist team or flexible price tied to actual document condition and exception volumes.

Choose D:  most resilient to unknown quality; should specify quantity-based, reviewed-hour or batch-based units and forbid unilateral expansion of scope.

# 4. Exactly what the factory delivers

## 4.1 Workflow and processing logic

### Controlled receipt

Receive source exports through permitted access; inventory source identifier, hash, original path, format, batch, readability, revision and disposition. Snapshots prevent silent scope drift.

### Parallel extraction

Use native text/CAD methods before OCR; retain originals and create separate searchable derivatives as applicable. Unsupported or unreadable items receive an explicit status rather than disappearing.

### Semantic extraction

Extract document number/title/revision and observed tags with source locations; normalize separately, retaining observed text and transformation rules.

### Candidate linking

Use CMMS/PI master lists, tag philosophy, train/unit rules, existing fuzzy candidates and selected LLM reasoning for hard cases. Reject unsafe highest-similarity-only decisions.

### Quality gates

Run deterministic checks on every applicable record; retain error categories, confidence/uncertainty, reviewer events and independent test results.

### Batch outputs

Export registers, evidence, reconciliation, raw/normalized records, exceptions, control totals, mappings and AIM load-ready files. Support representative trial loading.

## 4.2 Minimum evidence and disposition contract

Every candidate relationship should carry a stable identifier, source document and path, page/sheet (and coordinates where available), observed tag, normalized tag, proposed CMMS target, extracted context, method/model/rule/version, confidence band, validation state and supporting evidence reference. Every input, including failed and excluded items, must have status and batch lineage. Candidates must never be labelled “engineering validated” without the required human review.

## 4.3 What is outside source-remediation scope

Do not change original documents, engineering drawings, CMMS/PI source values, the customer asset hierarchy or create new engineering tags. This is broadly consistent with SOW §4.2. However, SOW §§8, 19–20 and 28 still require searchable derivative work where applicable, proper deliverable construction and correction of contractor-produced defects, including trial-load rejection caused by our outputs.

# 5. AI, technology and platform choices

## 5.1 Do not use expensive reasoning for commodity extraction

The preferred technology is a multi-lane processing architecture: native text and structured exports first; specialised OCR and layout detection for scanned files; deterministic tagging rules / fuzzy ranking for candidate generation; a capable multimodal LLM only for conflicts, ambiguous train-context questions, composite documents and complex metadata. This controls cost and makes decisions reproducible.

High-thinking models are not substitutes for authoritative tag dictionaries, validation rules or engineering judgement. A model should cite input evidence and have an explicit “unresolved” route when facts are insufficient. Do not pre-train or fine-tune indiscriminately on all source documents; defer fine-tuning until a pilot shows a persistent error category and quantifiable benefit.

## 5.2 Hosting/model options

| Option | Strength | Concern / decision |
| --- | --- | --- |
| Private enterprise-hosted LLM | Potentially strong complex-context reasoning without GPU operations. | Only if Oman LNG approves processing location, retention, telemetry, agreements and subprocessors. |
| Self-hosted Llama/Qwen/Mistral-class model | Direct control over model runtime, networking and storage. | Requires validated multimodal accuracy, compute capacity, ops, licensing review and performance benchmarks. |
| Deterministic + OCR baseline | Reproducible, comparatively economical and often suitable for most pages. | Weak on legacy ambiguity and unreadable drawing content; needs exception route. |

## 5.3 Reuse candidates: AHA/IDB, RDL Explorer and DataGate

Shell AHA/IDB experience may be relevant to bulk loading and tag-document relationships. RDL Explorer could support reference standards; DataGate could support governed staging, quality checks and controlled release. None should be assumed approved, maintained, interoperable or available to Oman LNG. Assess present security, maintenance, licence/IP rights, interfaces, export model and deployment economics before including them in the committed solution. Avoid creating a separate asset hierarchy or knowledge graph, which the SOW excludes without variation.

# 6. QA/QC design and meaningful acceptance metrics

## 6.1 Automated checks applied across the agreed population

Source control: counts, completeness, hash consistency, original-to-derivative references, duplicate and batch statuses.

Extraction integrity: text-layer availability, page and sheet coverage, structured metadata presence, method/version capture and OCR flags.

Engineering matching checks: tag structure, class, source existence, train/unit consistency, prohibited many-to-one assumptions and documented normalization.

Relationship integrity: unique IDs, referenced evidence, document revision, page location and referential integrity; maintain accepted/rejected/unresolved states.

Delivery quality: AIM field names, data types, controlled values, null rules, encoding, load sequence, schema conformance and trial-load validation.

The target is 100% application of defined automatic controls to eligible records, not 100% successful OCR, confidence or accuracy. An automatic check can fail and should then generate an auditable exception.

## 6.2 Independent manual assurance - four sampling strata

| Stratum | Purpose | Must establish |
| --- | --- | --- |
| A. Stratified source-document gold set | Detect missing tags, metadata and revision errors. | Recall as well as precision; capture silent false negatives. |
| B. Machine high-confidence candidates | Test calibration and avoid hidden false-positive clusters. | Precision and error distribution by format/class/train. |
| C. High-risk / low-confidence links | Resolve technical conflicts and prioritise severe consequences. | Engineering decisions with evidence and reviewer identity. |
| D. PI-to-CMMS and AIM load sample | Check cross-domain logic and downstream usability. | PI mapping metrics, schema conformity and batch acceptance. |

## 6.3 Acceptance categories must not be conflated

Automatically checked:  the system applied rules and passed mechanical validation; engineering correctness is not assured.

High confidence:  a candidate has a comparatively strong model/rule score; score does not prove validity.

Engineering reviewed:  a competent specialist has examined specified evidence and recorded a decision.

Customer accepted:  Oman LNG has approved the relationship or the batch under the agreed sign-off mechanism.

Unresolved / dispositioned:  a record remains unresolved with a formally approved exception outcome. Open issues cannot simply be hidden.

## 6.4 Suggested pilot measures

Measure tag-detection precision AND recall, metadata accuracy, revision-code/date accuracy, document-to-tag and PI-to-CMMS precision, exception frequency, manual-review time, per-format OCR conversion success, batch completeness and load-ready validity. Target thresholds, confidence bands and the accuracy-measurement method must be agreed in the mandatory pilot (SOW §§16–17). Do not set a single broad “95% AI accuracy” promise.

# 7. Review capacity and three data-quality scenarios

## 7.1 Paid time versus useful review output

The model purchases 4,800 specialist review hours at $50/hour ($240k). For planning, 75% is assumed productive time on review cases: 3,600 hours. The other 1,200 hours cover calibration, document retrieval, recheck coordination and mandatory review records. The QA lead receives a separate 600-hour budget, and is not treated as additional case-review capacity.

| Data quality | Candidate share with strong evidence* | Mean manual review duration | Indicative maximum cases from 3,600 productive hours |
| --- | --- | --- | --- |
| Decent | 85–95% | 5–8 minutes | 27,000–43,200 |
| Hybrid | 60–80% | 8–12 minutes | 18,000–27,000 |
| Really bad | 25–50% | 15–25 minutes | 8,640–14,400 |

* “Strong evidence” is an uncalibrated candidate share hypothesis, not automatic engineering acceptance. The reviewed counts are theoretical capacities and will fall if complex escalations, multiple pass reviews or recall studies are more demanding than assumed.

## 7.2 Why 500,000 candidate relationships changes the interpretation

For an illustrative population of 500,000 candidate relationship rows, central strong-candidate shares of 90% / 70% / 35% imply roughly 50,000 / 150,000 / 325,000 remaining weak, ambiguous or unresolved candidates. Under an $800k capped review model, no scenario assures that every weak relationship will receive individual manual adjudication. The correct contractual output is an accurately described mix of machine-check-passed, sampled, individually reviewed and unresolved records, with customer-approved disposition responsibilities.

## 7.3 Scenario-specific consequences and commercially sensible responses

### Decent: mostly native, searchable and consistent

The factory is likely to deliver high throughput, with modest OCR burden and fewer interpretation conflicts. Direct review capacity might cover many exceptions and sizeable independent samples. Remain cautious: near-perfect candidate scores must still be validated for false-negative omission and train-crossovers. Accept the $800k cap only if the pilot confirms the expected evidence distribution.

### Hybrid: mixed searchable, raster, historical and conflicting data

The base case for internal planning. Allocate independent gold samples to both quality extremes and prioritise high-consequence instrumentation and PI relationships. Manual engineering review must be prioritised by risk, not by unbounded backlog size. Unresolved records should be handed over to named Oman LNG owners under agreed decision SLAs.

### Really bad: poor scans, unsupported native formats and unreliable reference data

Most inputs can still be inventoried and subjected to processing attempts, but a large fraction may lack dependable evidence. The 3,600 productive review hours will cover relatively few cases. The rational response is to cap the QA programme, publish a transparent unresolved queue, propose extra review packages or seek client-led adjudication; do not silently promise complete engineering validation at $800k.

# 8. Bottom-up commercial model

## 8.1 Base factory - $320,000 estimated cost

| Component | Cost | Basis |
| --- | --- | --- |
| India-led factory labour, AI/data engineers and delivery management | $230,400 | Prior six-month factory estimate; not firm subcontractor rates. |
| OCR, inference, compute and licences | $45,000 | Capped allowance; architecture and page count unverified. |
| Security, interfaces and trial-load preparation | $12,000 | Assumes existing infrastructure and reusable components. |
| Base contingency and contractor-output rework | $32,600 | Only explicit reserve in the $640k combined cost model. |
| SUBTOTAL | $320,000 | Factory cost ceiling. |

## 8.2 Incremental assurance - $320,000 estimated cost

| Component | Cost | Basis |
| --- | --- | --- |
| Engineering and document QA reviewers | $240,000 | 4,800 paid hours at $50/h. |
| Senior QA/QC lead | $42,000 | 600 hours at $70/h. |
| QA automation, tests and dashboards | $25,000 | Acceptance rules, data-quality reporting and dashboards. |
| Independent reporting / AIM trial-load QA | $13,000 | Quality reports and validation support. |
| SUBTOTAL | $320,000 | No dedicated incremental QA contingency. |

## 8.3 Margin, not markup

| Metric | Amount | Explanation |
| --- | --- | --- |
| Delivery cost ceiling | $640,000 | Factory + QA/QC costs. |
| Target gross profit | $160,000 | 20% of $800,000 customer price. |
| Customer selling price | $800,000 | $640,000 / (1 - 20%). |

Commercial warning: only $32,600 (approximately 5.1% of total delivery cost) is explicit base contingency. Without scope caps and escalation controls, a fixed $800k price is exposed to material overrun.

## 8.4 Optional extension economics

A hypothetical additional $50,000 selling-price QA module at the same 20% gross margin provides $40,000 of cost budget. At $50/hour this buys up to 800 paid reviewer hours, or about 600 productive case-review hours at the 75% assumption, before any new mobilisation or lead support. Tender pricing of extra batches/pages/formats should instead be specified after pilot cost measurement; the module is an illustration, not an agreed rate.

# 9. People, roles and accountabilities

| Accountable role | Primary responsibility | Commercial assumption |
| --- | --- | --- |
| Prime contractor / bid owner | Contract, governance, AI security, deliverable acceptance, risk owner. | Small core leadership; not additional unlimited review team. |
| Engineering QA lead | Gold sample protocol, competency, calibration, reviewer escalation, evidence decisions. | 600 hours included at $70/h. |
| India-led specialists (e.g., L&T option) | Review I&C/process/electrical/mechanical and document-control samples; engineer exceptions. | 4,800 purchased hours at $50/h. |
| AI/data engineering factory | Native parsing, OCR, rules, LLM routing, batch logs and structured output. | Included in prior $320k factory budget. |
| Oman LNG data / engineering owners | Provide gold data, philosophy, engineering decisions, final approvals and AIM requirements. | Named SLA and decision rights are essential to alternative scope. |
| Customer cybersecurity / architecture | Approve models, data residency, subcontractors, interfaces and retention. | Approval before transfer or model processing. |

“I&C” means instrumentation and control; “process” refers to process engineering. “CMMS” is the maintenance asset system, “PI Historian” the time-series tag environment, and “AIM” the target asset information management model. The SOW seeks demonstrable domain competence for engineering validation; general data-labelers alone would not meet this requirement (SOW §18).

# 10. Delivery plan, gates and acceptance

| Gate | Evidence required | Decision / implication |
| --- | --- | --- |
| G0: Scope and security | Approved alternative RACI; volumes/quantity rules; processing environment; model terms. | Without approval, do not offer fixed capped validation. |
| G1: Pilot design | Stratified sample, customer gold standard, extraction rules and measurement protocol. | Measurement must include false negatives and all major document classes. |
| G2: Pilot acceptance | Precision/recall by type, exception yield, cost per page / link, projected QA load, AIM schema. | Freeze methodology or reprice before full production. |
| G3: Production batches | Balanced reconciliation, evidence and exceptions, documented QA sampling, versioned outputs. | Batch release follows approved quality gates and customer decisions. |
| G4: Trial load / handover | Schema/load integrity, correction of our defects, retained audit trail and open-issue disposition. | Final payment tied to agreed accepted outputs, not count processed alone. |

## 10.1 Proposed milestone weighting (negotiable)

An illustrative payment arrangement is 10% for approved mobilisation/methodology, 20% at accepted pilot, 25% at first accepted production batches, 25% at final production batches, and 20% at accepted trial load, QA report and handover. This is not the tender’s established payment schedule; adapt to section 29 and legal/commercial agreement.

## 10.2 Stop/go and change-control triggers

An agreed source/page/candidate cap is exceeded, a previously unknown proprietary format requires specialist integration, or approved reference data is materially incomplete.

Measured pilot precision/recall or engineering review effort makes the QA commitment infeasible at existing price, or low-quality documents exceed the agreed scenario band.

Oman LNG cannot provide secure processing approval, supported AIM targets, approved expert reviewers or timely disposition decisions.

The customer insists on full individual relationship validation, no unresolved handover, or acceptance terms identical to the original SOW without an associated full-scope quotation.

# 11. Tender qualifications, safeguards and key decisions

## 11.1 Wording needed in an alternative offer

### Contracted deliverable

Specify candidate relationship registers and separately identified engineering-reviewed records, evidence fields, machine QA results, exceptions and AIM-aligned outputs; explicitly define final acceptance status.

### Responsibility split

Name the party that validates ambiguous train/unit relationships and gives final technical approval; clarify who approves exception closure and what a valid bulk disposition means.

### Review-hour ceiling

Cap QA at 4,800 paid reviewer hours plus specified lead/testing budget; no implied obligation to manually verify every weak candidate.

### Volume and format envelope

Set limits on source documents, physical pages/sheets, proprietary file types, number of delivery batches, recurring extracts and independent review workload.

### Defect correction

We correct our own extraction, mapping, evidence and load-package defects at no extra fee where caused by failure to meet agreed contract; this is not original-source remediation.

### AI / information restrictions

Allow only approved locations/models/services, control prompt/log retention and data destruction, and confirm pre-existing proprietary IP and transfer of contract-specific outputs.

### Pilot thresholds and change mechanism

Set measurable QA metrics, approval gates, quality rebaseline and commercial change thresholds before production.

## 11.2 Consequence of failing to obtain the deviations

If Oman LNG requires the contractor to certify and resolve all relationships and obtain formal acceptance using the existing section 28 standard, the $800k capped model is not a safe firm fixed-price submission. Reprice the fully validated scope after pilot or state the $800k alternative as an explicit non-conforming bid, subject to procurement rules. Do not hide engineering validation as “automated” merely to preserve the price.

# 12. Risk management framework

Risk scores below are initial qualitative estimates for internal bid planning, not actuarial frequencies. Probability and severity must be revisited after pilot and as the contractual assumptions are confirmed. “Mitigation” denotes controls intended to prevent or reduce the risk; “remediation/response” denotes the steps taken if the risk occurs. No response presumes permission to edit Oman LNG original source data.

| Likelihood | Meaning | Impact | Meaning |
| --- | --- | --- | --- |
| Low | Unlikely with current assumptions | Moderate | Local rework; controllable within approved reserve. |
| Medium | Plausible; material uncertainty remains | High | Major QA, cost, timeline or acceptance consequences. |
| High | Likely or actively expected unless addressed | Critical | May invalidate bid, breach data controls or defeat price ceiling. |

Risk ownership: named accountable lead; trigger: objectively observable condition; mitigation: pre-emptive control; response: approved corrective action or commercial rebaseline.

# 13. Detailed risk register

Sixteen priority risks are identified below. Likelihood and impact ratings are initial inherent ratings before the proposed controls. Each risk record includes a distinct prevention/mitigation strategy and an occurrence/remediation response.

## R01  Tender deviation or capped validation rejected

Likelihood: High     Impact: Critical     Owner: Bid director / legal

Risk / consequence:  Original SOW holds the contractor responsible for validated relationships and acceptance; $800k alternative could be non-compliant or rejected outright.

Mitigation (before):  Ask formally whether variant bids are permitted; secure signed responsibility/RACI, manual QA cap, exception protocol and quality-based acceptance; maintain a separate full-scope option.

Remediation / response (after):  Reprice full validation after the pilot, seek an authorised contract variation, or issue a documented no-bid decision.

Trigger / indicator:  Procurement requests full engineering sign-off without price revision.

## R02  Document estate far worse than pilot sample

Likelihood: High     Impact: Critical     Owner: Technical architect / QA lead

Risk / consequence:  Very poor OCR, proprietary drawings or conflicting revisions expand exception volumes, rendering the capped QA insufficient.

Mitigation (before):  Stratify pilot by type, age, train, supplier and known difficult categories; sample composite drawings and unreadable files.

Remediation / response (after):  Publish failed/low-confidence status; pause batch release, renegotiate scope or invoke the agreed extra-review/module rate.

Trigger / indicator:  Actual conversion failure / exception share breaches agreed pilot band.

## R03  Physical pages and relationship rows far exceed assumed quantities

Likelihood: Medium     Impact: High     Owner: Delivery manager / commercial lead

Risk / consequence:  150k files may contain millions of pages and very many sightings; compute, review and handover sizes can exceed priced limits.

Mitigation (before):  Inventory pages/sheets, composite sub-documents and expected candidate volume; establish firm caps and overage rates.

Remediation / response (after):  Freeze dataset and obtain change order for incremental batches/volumes, or return unsupported excess as explicitly authorised exceptions.

Trigger / indicator:  Page/sheet or candidate count crosses contracted thresholds.

## R04  False positive technical mappings, including train crossovers

Likelihood: High     Impact: High     Owner: Engineering QA lead

Risk / consequence:  Incorrect tag-to-document or PI mappings may affect equipment interpretation, downstream asset search and trust in the register.

Mitigation (before):  Use approved tagging philosophy, train/unit constraints, non-1:1 cardinality rules, evidence-linked scoring and blind engineering samples.

Remediation / response (after):  Quarantine affected batch, correct matching algorithm/output, rerun/recheck impacted records and report residual uncertainty.

Trigger / indicator:  Reviewed sample finds systematic cross-train, class or function mismatches.

## R05  False negatives hidden by a candidate-only review

Likelihood: Medium     Impact: High     Owner: QA analytics lead

Risk / consequence:  Tags or document relationships omitted by extraction may never enter the review queue, overstating coverage or recall.

Mitigation (before):  Build document-level gold samples that compare against original sources, not just model-proposed candidates; measure recall separately.

Remediation / response (after):  Adjust native parser/OCR rules and reprocess relevant source classes; report measured omissions and revised QA metrics.

Trigger / indicator:  Measured recall misses agreed gate despite high precision.

## R06  Oman LNG data security, AI usage or India subcontractor approval fails

Likelihood: Medium     Impact: Critical     Owner: Information security lead

Risk / consequence:  Data residency, privacy, telemetry, public AI use or unapproved offshore access can block delivery or create a contractual incident.

Mitigation (before):  Get written approval of service, hosting geography, encryption, logging, deletion, model retention and all subcontractors before data access.

Remediation / response (after):  Stop affected processing, follow incident/containment process if necessary, move to an approved architecture and rebaseline schedule/cost.

Trigger / indicator:  Security committee rejects platform or flags unauthorised transfer.

## R07  Customer engineering decisions and approvals are slow

Likelihood: High     Impact: High     Owner: Client interface lead

Risk / consequence:  An unresolved queue blocks exception dispositions, pilot approval, batch sign-off and contractor cash flow.

Mitigation (before):  RACI with named approvers, response SLA, decision backlog dashboard and accepted bulk-disposition categories.

Remediation / response (after):  Escalate stalled decisions; reschedule / invoke contractual customer-dependency relief; maintain full unresolved audit trail.

Trigger / indicator:  Aging backlog or approval SLA breach.

## R08  AIM target schema or trial load reveals our deliverable defects

Likelihood: Medium     Impact: High     Owner: Data lead / AIM specialist

Risk / consequence:  Files may be rejected due to identifiers, mandatory fields, relationship cardinality or target controlled values.

Mitigation (before):  Get approved target schema early; validate data types, FKs, controlled values and sequence; run trial load before full batch.

Remediation / response (after):  Correct and regenerate our delivery package without charge where required by the agreed contract, then resubmit and reconcile.

Trigger / indicator:  Trial load rejects contractor-generated records or batch.

## R09  OCR, inference and GPU/cloud costs exceed $45k allowance

Likelihood: Medium     Impact: High     Owner: AI engineering lead

Risk / consequence:  High page count, repeated runs or excessive advanced LLM calls erode the narrow reserve and 20% margin.

Mitigation (before):  Prioritise native/rules extraction; use small models, cached results, fixed cost budgets, per-lane metrics and provider spending caps.

Remediation / response (after):  Throttle or reroute inference, stop non-essential processing, seek priced extension for material input growth, optimise and rerun required defect corrections.

Trigger / indicator:  Unit compute cost or forecast breaches budget threshold.

## R10  Legacy/proprietary CAD and composite files cannot be read

Likelihood: High     Impact: High     Owner: Document-processing lead

Risk / consequence:  SmartPlant/MicroStation/AutoCAD native variants and vendor books can require specialist parsers or licences.

Mitigation (before):  Inventory exact versions early; test native readers on pilot; preserve file-level lineage, record unsupported outcomes and limits.

Remediation / response (after):  Engage approved specialist converter through variation or mark as conversion exceptions with customer-approved disposition.

Trigger / indicator:  Native-reader failure rate rises above acceptable threshold.

## R11  Inadequate reference data, tag philosophy or gold-standard labels

Likelihood: Medium     Impact: High     Owner: Engineering QA lead / client data owner

Risk / consequence:  Without approved dictionaries, tagging conventions and validated samples, confidence and QA claims are not defensible.

Mitigation (before):  Request all SOW §5 inputs at mobilisation; co-create representative reference set and exception policies; freeze approved rules.

Remediation / response (after):  Restrict claims to measured segments; defer affected releases; obtain decisions on ambiguous standards and rebaseline pilot.

Trigger / indicator:  No agreed gold standard / tag conventions at pilot sign-off.

## R12  Source data refresh, late additions and revision drift

Likelihood: Medium     Impact: High     Owner: Source control lead

Risk / consequence:  Incremental updates invalidate hashes, sampling, mappings and cost baselines; old/new revisions create duplicate or contradictory links.

Mitigation (before):  Freeze extract cut-off, timestamped batch inventory, hash, repeatability and formal scope change.

Remediation / response (after):  Run a separately priced delta batch, remap impacted records and issue versioned change log; do not overwrite source history.

Trigger / indicator:  Late incoming files or changed register hashes after source freeze.

## R13  QA reviewer rate, availability or productivity assumptions fail

Likelihood: Medium     Impact: High     Owner: Resource / commercial lead

Risk / consequence:  Specialist LNG I&C/process review may cost more than $50/h, or 75% productive review time may not be achieved.

Mitigation (before):  Seek supplier quotes, stratify review tasks, monitor minutes per decision, reviewer agreement and calibration during pilot.

Remediation / response (after):  Reallocate within approved QA budget, prioritise critical sample, or propose an authorised paid review module.

Trigger / indicator:  Effective hours or rate diverges materially from model.

## R14  Insufficient headroom for contractor-caused output rework

Likelihood: High     Impact: High     Owner: Delivery director

Risk / consequence:  Combined budget has only $32.6k explicit contingency; correction and resubmission duties can exhaust profitability.

Mitigation (before):  Automated unit/integration tests, canary batches, golden runs, change control for external changes and cost-to-complete reporting.

Remediation / response (after):  Use reserve for our rework, remove root cause, regenerate and resubmit; escalate any non-defect variation for approval.

Trigger / indicator:  Rework burn rate exhausts reserve or persistent defect pattern emerges.

## R15  Intellectual property, third-party licences or platform reuse blockers

Likelihood: Medium     Impact: Moderate     Owner: Solution architect / legal

Risk / consequence:  Pre-existing tools or Shell platforms may be restricted, unsupported or incompatible with client ownership/hand-over requirements.

Mitigation (before):  Validate licence, transfer, support and security rights before proposal; contractually list pre-existing vs project-specific IP.

Remediation / response (after):  Replace component or licence via approved change; deliver sufficient rules/configuration to meet handover obligations.

Trigger / indicator:  Third-party IP or vendor rejects intended use/transfer.

## R16  Client cannot accept unresolved status or capped quality warranty

Likelihood: High     Impact: Critical     Owner: Bid director / client sponsor

Risk / consequence:  The tender may require accepted, individually validated relationships across the population; candidate-only outcomes fail contract.

Mitigation (before):  Explicit acceptance specification, disaggregated statuses, agreed measurable QA thresholds and signed alternative bid boundary.

Remediation / response (after):  Offer larger verification service with scenario-priced fee or revert to full-scope bid; do not mislabel candidates as validated.

Trigger / indicator:  Client confirms no outstanding engineering decisions allowed.

# 14. Risk response by data-quality scenario

## Decent

Proceed with the standard $800k base only after the pilot establishes acceptable precision/recall and successful native extraction across representative classes. Use spare QA capacity for confidence calibration, cross-train risks and blind sampling; preserve the right to reject unsupported claims despite generally good quality.

## Hybrid

Treat as the operational base scenario. Segment by document class and train, measure reviewers by high-consequence relationships and maintain a weekly decision backlog with the customer. Protect the $800k ceiling by explicitly capping review-hours and accepted source quantities.

## Really bad

Activate a triage mode: prioritise critical equipment and instrumentation, preserve all unreadable/unsupported statuses, give quantified missing-data reports and require approved dispositions. Avoid assuming the factory can “repair” damaged originals. Offer review extension modules only after the customer confirms additional budget and timeline.

## Catastrophic acceptance or security deviation

Suspend irreversible data processing or final pricing commitment if security approval, right to use AI/subcontractors, or transfer of engineering sign-off is rejected. The correct commercial response is a reprice / alternative delivery architecture / no-bid, not weakening audit trails or silently lowering accuracy thresholds.

# 15. Tender clarifications to submit

## Scope, volumes and reference data

What is the actual page/sheet count and percentage of native vs raster formats, including composite dossiers and CAD file versions?

Are maintenance items beyond CMMS tag records included? Which asset classes and PI calculated / virtual tags must be included or excluded?

Is a customer-approved gold-standard pilot sample and tagging philosophy available, and who resolves inconsistent source references?

## Technical acceptance and responsibilities

Will Oman LNG accept a separately labelled AI factory + capped QA alternative, with final engineering verification by its appointed SMEs?

Can ambiguous/unsupported items be formally accepted as exceptions with a recorded disposition, rather than contractor-led source repair?

What precision and recall thresholds, separate per document/tag class, will be established after pilot? Can acceptance focus on measured evidence and load-ready structure?

What does “contractor correction at no cost” cover when root cause is incomplete client source data vs a demonstrable supplier-generated defect?

## AI, environment, platforms and IP

Which hosting geography, model services, GPU infrastructure, data retention, subcontractor locations and audit logging are approved?

Which versions of AVEVA AIM templates, schema and trial environment will be provided? Are customer licences/engineering viewers available?

Are AHA/IDB or other Shell assets viable for reuse, subject to support and IP approval? If so, who sponsors the decision?

## Commercial, governance and timing

Are alternative proposals and milestone payments tied to pilot and batch acceptance permitted by procurement rules?

How many reviewer hours / customer engineering decisions are expected, and what review SLA and approved change-order mechanism can be agreed?

Can source/page/batch limits, late additions and unsupported proprietary formats trigger separately priced variation?

# 16. Decision log and next actions

| Decision | Recommendation | Consequence if declined |
| --- | --- | --- |
| D01 $800k target + 20% margin | Keep as bid objective, not binding quote until pilot / scope sign-off. | Rebaseline or no-bid if firm price cannot be supported. |
| D02 Customer final sign-off | Request written alternative RACI and exception disposition ownership. | Need full validation model and larger commercial budget. |
| D03 QA capacity cap | 4,800 paid reviewer h + 600 QA lead h; documented sampling plan. | Exposure to unbounded labour and acceptance risk. |
| D04 No source remediation | Explicitly exclude modifying original data; correct our own outputs. | Scope ambiguity and potential unpriced repair work. |
| D05 AI / provider selection | Choose after approved hosting and head-to-head pilot on cost/quality. | Cyber, model cost and IP risks. |
| D06 Quantity and format guardrails | Price by agreed batch population/pages and supported input classes. | Page explosion and compute-cost overruns. |
| D07 Pilot go/no-go | Require client approval of quality and output model before production. | Cannot defend quality metrics or $800k economics. |

## Proposed immediate next actions

Agree internally whether the $800k offer is positioned as an alternative tender option or the only response; confirm bid permissibility with procurement.

Request short written customer clarification on engineering validation ownership, acceptable unresolved cases, and the exclusion of source data remediation.

Obtain sample files across format / age / train / condition and client reference extracts; design the stratified gold-standard pilot.

Obtain indicative L&T/offshore reviewer and AI-processing supplier quotes; confirm secure location and interface permissions.

Refine cost-to-complete, QA sampling hours, SLA, review extension rate and contractual acceptance wording using pilot data.

# 17. Appendix — tender traceability and terminology

| SOW section | Requirement / relevance | Where addressed |
| --- | --- | --- |
| §2 / §4 | Population, format scope and explicit exclusions. | Sections 2, 4, 7, 11, 15. |
| §§6–13 | Source reconciliation, OCR, metadata, tags, relationship and evidence registers, PI matching. | Sections 4–6. |
| §15 | Exception register and approved close-out. | Sections 6, 11, 13. |
| §§16–18 | Mandatory pilot, accuracy measurement, human engineering validation. | Sections 6–7, 9–11. |
| §§19–20 | AVEVA AIM-aligned machine output and trial-load corrections. | Sections 4, 6, 10, 13. |
| §§21–23 | Methodology, AI security restrictions, IP and reproducibility. | Sections 5, 11, 13. |
| §§24–25 / §§27–30 | Responsibilities, deliverables, acceptance, payment milestones and change control. | Sections 3, 9–16. |

## Acronym guide

| Term | Meaning |
| --- | --- |
| AI / LLM / OCR | Artificial Intelligence / Large Language Model / Optical Character Recognition. |
| CMMS | Computerized Maintenance Management System: authoritative maintenance / asset register. |
| PI Historian | Industrial operational-time-series historian and associated tag register. |
| QA / QC | Quality Assurance / Quality Control: process confidence vs checking outputs. |
| I&C / Process | Instrumentation & Control engineering / Process engineering. |
| AIM / ETL / CAD | Asset Information Management / Extract-Transform-Load / Computer-Aided Design. |
| RACI | Responsible, Accountable, Consulted, Informed: decision-rights matrix. |

## Source and limitations

Oman LNG LLC, Scope of Work v2, 41-page user-provided tender specification (authoritative tender basis). Commercial numbers, AI throughput, reviewer-productivity factors, candidate confidence percentages, platform shortlist and risk likelihoods are internal planning hypotheses derived for discussion, not validated customer facts. Previous presentation iterations are working assumptions only, not independent corroboration.